## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US1 | As a team, we need to plan project workflow so that all teams can work in coordination | MUST HAVE | None | Coordination Team | 3- Completed
Sprint 1 | Sprint 1 | US2 | As a system, we need an English dataset for initial model training | MUST HAVE | None | Data Team | 3- Completed
Sprint 1 | Sprint 1 | US3 | As a system, we need clean and preprocessed data for model training | MUST HAVE | US2 | Data Team | 3- Completed
Sprint 2 | Sprint 2 | US4 | As a system, we need a trained model for ticket classification | MUST HAVE | US3 | Model Team | 3- Completed
Sprint 2 | Sprint 2 | US5 | As a system, we need structured ticket generation (title, category, priority, entities) | MUST HAVE | US4 | Model Team | 3- Completed
Sprint 2 | Sprint 2 | US6 | As a system, we need backend APIs to process tickets | MUST HAVE | None | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US7 | As a system, we need a database to store user and ticket data | MUST HAVE | US6 | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US8 | As a user, I want a UI to submit complaints easily | MUST HAVE | None | Frontend Team | 3- Completed
Sprint 2 | Sprint 2 | US9 | As a user, I want to view AI-generated ticket results | MUST HAVE | US8 | Frontend Team | 3- Completed
Sprint 3 | Sprint 3 | US10 | As a system, we need to integrate model with backend APIs | MUST HAVE | US4, US6 | Backend Team | 2- In Progress
Sprint 3 | Sprint 3 | US11 | As a system, we need to connect frontend with backend APIs | MUST HAVE | US6, US8 | Backend Team | 2- In Progress
Sprint 3 | Sprint 3 | US12 | As a user, I want voice input for ticket submission | SHOULD HAVE | US8 | Satla Prayukthika | 2- In Progress
Sprint 3 | Sprint 3 | US13 | As a system, we need end-to-end integration | MUST HAVE | US10, US11 | Asmeet Kaur Makkad | 2- In Progress
Sprint 3 | Sprint 3 | US14 | As a system, we need system testing and debugging | MUST HAVE | US13 | Asmeet Kaur Makkad / Duniya Vasa | 1- Yet to Start
Sprint 3 | Sprint 3 | US15 | As a system, we need multilingual support using Google Translate for diverse inputs | SHOULD HAVE | US4 | Satla Prayukthika | 2- In Progress
Note on F1: ====== ID#AAABzZb1gx0 Sumeet Kumar Barua08 (2026-02-10 14:37:18) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 3 BACKLOG
US10 | T1 | Integrate model with backend API | 2026-03-10 | 2026-03-15 | Asmeet Kaur Makkad | Integration | Pending | 12 | 2 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US11 | T2 | Connect frontend with backend APIs | 2026-03-12 | 2026-03-18 | Dinesh Reddy Vasampelli | Integration | Pending | 10 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US12 | T3 | Implement voice input feature | 2026-03-10 | 2026-03-16 | Satla Prayukthika | Development | In Progress | 8 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US15 | T4 | Integrate Google Translate for multilingual support | 2026-03-12 | 2026-03-20 | Bandi Keerthi Krishna | Integration | In Progress | 8 | 0 | 0 | 1 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US13 | T5 | Perform full system integration | 2026-03-15 | 2026-03-21 | Asmeet Kaur Makkad | Integration | Pending | 12 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
US14 | T6 | System testing and debugging | 2026-03-21 | 2026-03-23 | Asna Abdul Kareem | Testing | Pending | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0
US1 | T7 | Project coordination and review | 2026-03-01 | 2026-03-23 | Duniya Vasa | Management | Ongoing | 10 | bar: Day 1 to Day 14
US1 | T8 | Coordination support and tracking | 2026-03-01 | 2026-03-23 | Sowjanya N | Support | Ongoing | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABzZb1gxY Please enter the dates in either of these formats (2026-02-10 14:37:18) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABzZb1gxg Please enter the dates in either of these formats (2026-02-10 14:37:18) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABzZb1gx8 Sumeet Kumar Barua08 (2026-02-10 14:37:18) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABzZb1gxQ Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABzZb1gxA Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABzZb1gxs Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABzZb1gxE Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABzZb1gxk Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABzZb1gyA Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABzZb1gxI Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABzZb1gx4 Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABzZb1gxo Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABzZb1gxw Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABzZb1gxM Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABzZb1gxU Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABzZb1gxc Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABzZb1gw8 Sumeet Kumar Barua08 (2026-02-10 14:37:18) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 2026-02-08 | Initial project scope and workflow unclear | Defined project plan, roles, and workflow
Sprint 1 | 2026-02-16 | Unclear dataset structure and categories | Standardized dataset format and categories
Sprint 1 | 2026-02-23 | Noisy and unstructured data during collection | Applied NLP preprocessing techniques
Sprint 1 | 2026-03-02 | Duplicate and inconsistent data entries | Performed data cleaning and validation
Sprint 2 | 2026-03-08 | Model setup and dependency issues | Installed required libraries and configured environment
Sprint 2 | 2026-03-15 | Model loading and parsing errors | Switched to local model loading and fixed parsing logic
Sprint 2 | 2026-03-16 | Frontend and backend not connected | Used mock data and prepared API structure
Sprint 3 | 2026-03-22 | Integration not initiated earlier | Planned integration workflow and task allocation
Sprint 3 | 2026-03-23 | Multilingual handling and incomplete integration | Integrated Google Translate and scheduled testing

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member Names | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 2026-02-03 | 2026-02-20 | Data Team | Structured dataset creation | Random/unstructured data | Data preprocessing practices | Clean English dataset prepared
2 | Sprint 2 | 2026-02-21 | 2026-03-10 | Model + Dev Teams | Parallel system development | Dependency delays | Team collaboration | Model + system developed
3 | Sprint 3 | 2026-03-11 | 2026-03-23 | Entire Team | Early integration & multilingual support | Late integration start | Coordination across teams | Planned integration + testing

## Unit Test Plan
Test Case ID | Module | Test Case Name | Test Procedure | Condition to be Tested | Expected Result | Actual Result | Status | Assigned To
TC-M-001 | ClassifierService | Critical Priority Mapping | Call predict('Blue screen after Windows update'). Check 'priority'. | Subcategory maps to PRIORITY_MAP['Blue Screen'] | priority == 'Critical' | priority == 'Critical' | Pass | Asna Abdul Kareem
TC-M-002 | ClassifierService | Network Team via Regex Override | Call predict('VPN connection issue'). Inspect 'assigned_team' and confidence. | Text contains 'VPN' — tech_keywords override fires | assigned_team == 'Network Support', confidence >= 0.92 | assigned_team == 'Network Support', confidence = 0.92 | Pass | Pragati Tiwari
TC-M-003 | ClassifierService | Auto-Resolve — Password Reset | Call predict('Forgot my password'). Check 'auto_resolve' flag. | Subcategory 'Password Reset' is in AUTO_RESOLVE_SUBS | auto_resolve == True | auto_resolve == True | Pass | Ippili Raju
TC-M-004 | ClassifierService | Missing Model Files — Error Raised | Point SAVE_DIR to empty folder. Call predict(). Observe. | model.safetensors absent | FileNotFoundError with descriptive message | FileNotFoundError raised correctly | Pass | Shaik Eshak
TC-M-005 | NERService | IP Address Regex Extraction | Call extract_entities('Server at 192.168.1.100 unreachable'). | IPv4 pattern matches regex; entity not in model output | Entity: {text:'192.168.1.100', label:'IP_ADDRESS', confidence:0.99} | Correct entity returned | Pass | Vinitha Giri
TC-M-006 | NERService | No Duplicate Entities | Provide text where model AND regex detect same entity. Count output. | Both layers extract same entity text | Entity appears exactly once | Single entity in output | Pass | Ritesh Bonthalakoti
TC-M-007 | NERService | Empty Input — Returns Empty List | Call extract_entities(''). | words list empty after split() | Returns [] | Returns [] | Pass | Asna Abdul Kareem
TC-M-008 | DuplicateService | Semantic Duplicate Detected | Add T1 'VPN not connecting'. Check T2 'Cannot connect to VPN'. | Cosine similarity >= 0.70 | is_duplicate == True, similarity >= 0.70 | is_duplicate = True, similarity = 0.83 | Pass | Pragati Tiwari
TC-M-009 | DuplicateService | Unrelated Tickets — No False Positive | Add T1 'Printer broken'. Check T2 'Database server down'. | Similarity < 0.70 | is_duplicate == False | is_duplicate = False | Pass | Ippili Raju
TC-M-010 | DuplicateService | Persistence After Restart | Add 3 tickets. Create new DuplicateService. Call load(). Check count. | knowledge_base.json exists with 3 entries | New instance loads 3 tickets from disk | 3 tickets reloaded | Pass | Vinitha Giri
TC-B-001 | GeminiService | Fallback When API Key Missing | Set GEMINI_API_KEY=''. Call get_summary('Test text'). | _initialized == False | Returns first 100 chars + ellipsis; no exception | Fallback text returned correctly | Pass | Asmeet Kaur Makkad
TC-B-002 | GeminiService | Bug Report — Plain Text Output | Call analyze_bug_report() with real report. Check for markdown symbols. | Gemini may return ** or ## markers | No markdown in response after post-processing | Clean plain text confirmed | Pass | Manya Sahasra
TC-B-003 | FastAPI /classify | Valid Ticket Returns Full Payload | POST {text:'Laptop screen flickering'} to /classify. | All AI services return data | 200 OK with: category, subcategory, priority, team, auto_resolve, confidence, entities, summary | All fields present; latency 287ms | Pass | Asmeet Kaur Makkad
TC-B-004 | FastAPI /classify | Empty Text — HTTP 422 | POST {text:''} to /classify. | Pydantic validation blocks empty string | HTTP 422 Unprocessable Entity | 422 returned with validation detail | Pass | Dinesh Reddy Vasampelli
TC-B-005 | FastAPI /classify | Response Time Under 500ms | POST 150-word ticket. Measure latency over 10 runs. | Models pre-loaded; normal server load | Average latency < 500ms | Average latency: 287ms | Pass | Vijayalakshmi S R
TC-F-001 | Ticket Form | Empty Submission Blocked | Open ticket page. Click Submit with all fields empty. | Mandatory description field is empty | Error message shown; no API call made | Validation error shown; no network request | Pass | Satla Prayukthika
TC-F-002 | Ticket Form | Short Description Rejected | Type 'help' (4 chars) in description. Click Submit. | Description < 10 chars minimum | Error: 'Please describe your issue in more detail' | Inline error displayed | Pass | Bandi Keerthi Krishna
TC-F-003 | Authentication | Company Signup → Pending Approval | Register with company domain (e.g. riteshprivatelimited.com). | Company domain detected by Signup.jsx | Redirect to PendingApproval page with WhatsApp contact link | PendingApproval screen shown with correct link | Pass | Shubha G D
TC-F-004 | Admin Dashboard | Tickets Filtered by Company (RLS) | Log in as Company Admin. Open Admin Dashboard. | Supabase RLS only returns tickets for admin's company | Dashboard shows only company-specific tickets | Only company tickets displayed | Pass | Bandi Keerthi Krishna
TC-D-001 | Training Dataset | No Null Values in text/label Columns | Load training CSV. Run df[['text','label']].isnull().sum(). | text and label columns must be fully populated | 0 null values in both columns | 0 nulls found after preprocessing | Pass | Praneetha Baru
TC-D-002 | Training Dataset | Label Count Matches id2label.json | Get unique labels from CSV. Compare with id2label.json keys. | All CSV labels must exist in trained model's label map | No label mismatch | All 24 labels matched correctly | Pass | Kavin Sarvesh
TC-D-003 | Training Dataset | No Majority Class > 60% | Count rows per category. Calculate % per label. | Dataset balanced enough for fair model training | No single category exceeds 60% of total samples | Max category 31%; distribution acceptable | Pass | Utukuri Naga Sri Hari Chandana