## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status | Remarks
D-001 | QA Team | 2026-03-05 | Stress meter gauge stuck at static 60% value on live dashboard despite backend updates. | Sprint 4 | Frontend Team | UI/Integration | Piped the real-time numeric stress score from AI fusion engine to the frontend component. | 2026-03-06 | Closed | Mismatch between stress_index payload and prop names resolved.
D-002 | UX Review | 2026-03-08 | Voice input button is too subtle and lacks visual feedback during recording. | Sprint 5 | Frontend+Backend Team | Usability | Implemented Siri-style wave animations and enlarged the microphone trigger for better visibility. | 2026-03-09 | Closed | Transformed into a premium Voice Assistant feature.
D-003 | QA Team | 2026-03-10 | Captured screenshot in bug report widget renders as a black image on specific displays. | Sprint 5 | Frontend Team | Functional | Fixed html2canvas transparency and CORS settings during capture process. | 2026-03-11 | Closed | Retested on all major environments successfully.
D-004 | Admin user | 2026-03-12 | General users are overwhelmed by the multiple dropdowns in the Bug Report widget. | Sprint 5 | Frontend Team | UX | Split widget into a simple mode for public routes and advanced mode inside user profiles. | 2026-03-13 | Closed | Auto-generating bug titles in simple mode based on description.
D-005 | Backend Team | 2026-03-13 | Classifier V3 failing to accurately categorize tickets containing mixed languages (Hinglish). | Sprint 6 | Model Team | Algorithmic | Retrained classifier with an expanded multilingual edge-case dataset. | 2026-03-13 | Closed | Undergoing testing in the staging environment.
D-006 | QA Team | 2026-03-15 | Contact Sales form dropdown for company size reverts to default on page refresh. | Sprint 6 | Frontend Team | Functional | Updated the state management to correctly persist custom dropdown values to local storage. | 2026-03-15 | Closed | Dropdown selections are now correctly retained.
D-007 | Ritesh Bonthalakoti | 2026-03-18 | Classifier V3 confidence boosted to 0.92 via regex override even when base prediction is low, masking real model uncertainty. | Sprint 3 | Asna Abdul Kareem | Logical | Added confidence cap review; regex override now only applies when category matches key technical signals and base confidence is above 0.6. | 2026-03-19 | Closed | Tested with 15 ambiguous inputs. False-high confidence eliminated.
D-008 | Asmeet Kaur Makkad | 2026-03-18 | NER service regex patterns (HOSTNAME, IP_ADDRESS) duplicating entities already extracted by the DistilBERT token classifier. | Sprint 3 | Dinesh Reddy Vasampelli | Logical | Added deduplication check in extract_entities(): new regex matches are skipped if a semantically identical entity exists in model output. | 2026-03-20 | Closed | Retest passed. No duplicate entity fields in ticket output.
D-009 | Satla Prayukthika | 2026-03-19 | Ticket form does not block submission when all fields are empty — sends empty payload to backend API. | Sprint 3 | Bandi Keerthi Krishna | User Interface | Added client-side validation gate in TicketForm.jsx; API call is blocked until mandatory fields (description ≥ 10 chars) are filled. | 2026-03-20 | Closed | Validated across Chrome, Firefox, and Edge.
D-010 | Vijayalakshmi S R | 2026-03-20 | DuplicateService in-memory store is cleared on every server restart; no persistence between sessions. | Sprint 3 | Asmeet Kaur Makkad | Maintainability | DuplicateService.load() now re-reads knowledge_base.json on startup and re-encodes all stored tickets. Verified persistence across Uvicorn restarts. | 2026-03-21 | Closed | 10 tickets pre-seeded; duplicate check correctly matched on restart.
D-011 | Praneetha Baru | 2026-03-22 | Multilingual input (Telugu + English mixed) falls through NER regex and model with 0 entities, causing empty metadata in ticket. | Sprint 3 | Shaik Eshak | Logical | Added transliteration pre-processing step before NER pipeline. Gemini fallback entity extraction triggered when NER returns empty list. | 2026-03-23 | Open | Partial fix applied. Edge cases in Hinglish remain under review.
D-012 | Kavin Sarvesh | 2026-03-23 | GeminiService get_summary returns raw Gemini response including markdown symbols (* ** etc.) which appear in the UI ticket card. | Sprint 3 | Ritesh Bonthalakoti | User Interface | Added a markdown-strip post-processor in gemini_service.py after response.text.strip(). | 2026-03-23 | Open | Fix deployed. Awaiting final UX sign-off from Satla Prayukthika.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others