## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status | Remarks
D-001 | QA Team | 2026-03-05 | Stress meter gauge stuck at static 60% value on live dashboard despite backend updates. | Sprint 4 | Frontend Team | UI/Integration | Piped the real-time numeric stress score from AI fusion engine to the frontend component. | 2026-03-06 | Closed | Mismatch between stress_index payload and prop names resolved.
D-002 | UX Review | 2026-03-08 | Voice input button is too subtle and lacks visual feedback during recording. | Sprint 5 | Frontend+Backend Team | Usability | Implemented Siri-style wave animations and enlarged the microphone trigger for better visibility. | 2026-03-09 | Closed | Transformed into a premium Voice Assistant feature.
D-003 | QA Team | 2026-03-10 | Captured screenshot in bug report widget renders as a black image on specific displays. | Sprint 5 | Frontend Team | Functional | Fixed html2canvas transparency and CORS settings during capture process. | 2026-03-11 | Closed | Retested on all major environments successfully.
D-004 | Admin user | 2026-03-12 | General users are overwhelmed by the multiple dropdowns in the Bug Report widget. | Sprint 5 | Frontend Team | UX | Split widget into a simple mode for public routes and advanced mode inside user profiles. | 2026-03-13 | Closed | Auto-generating bug titles in simple mode based on description.
D-005 | Backend Team | 2026-03-13 | Classifier V3 failing to accurately categorize tickets containing mixed languages (Hinglish). | Sprint 6 | Model Team | Algorithmic | Retrained classifier with an expanded multilingual edge-case dataset. | 2026-03-13 | Closed | Undergoing testing in the staging environment.
D-006 | QA Team | 2026-03-15 | Contact Sales form dropdown for company size reverts to default on page refresh. | Sprint 6 | Frontend Team | Functional | Updated the state management to correctly persist custom dropdown values to local storage. | 2026-03-15 | Closed | Dropdown selections are now correctly retained.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others